## Лист1
Gantt Plan for Weeks 7–10 (Milestone 1 – Handbook of Programming Languages)
Task | Responsible | Week 7 | Week 8 | Week 9 | Week 10
Define project theme and write Project Proposal | Almukhammed
Create Use-Case diagram | Almukhammed
Create ERD and UML diagrams | Adil
Set up Git repository and initial commit | Almukhammed
Create Gantt plan | Arman
Write and format README.md | Arman
Prepare code skeleton (go.mod + main.go) | Almukhammed
Collect all files and create ZIP archive | Arman
Implement structs (Language, Category, Entry) | All
Implement endpoints (POST /language, GET /search) | Adil
Add search functionality | Adil
Add view statistics feature | Almukhammed
Implement basic testing and debugging | All